## GanttChart
WBS for Performance and Salary Management System | [9 empty] | Gantt Chart Template © 2006-2018 by Vertex42.com.
Federated Insurance
| Project Start Date | 2023-09-17 |  |  |  | Display Week | 1 |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15
| Project Lead | [8 empty] | 2023-09-18 | [6 empty] | 2023-09-25 | [6 empty] | 2023-10-02 | [6 empty] | 2023-10-09 | [6 empty] | 2023-10-16 | [6 empty] | 2023-10-23 | [6 empty] | 2023-10-30 | [6 empty] | 2023-11-06 | [6 empty] | 2023-11-13 | [6 empty] | 2023-11-20 | [6 empty] | 2023-11-27 | [6 empty] | 2023-12-04 | [6 empty] | 2023-12-11 | [6 empty] | 2023-12-18 | [6 empty] | 2023-12-25
 | time axis 2023-09-18 to 2023-12-31
WBS | TASK | LEAD | PREDECESSOR | START | END | DAYS | % DONE | Effort in Hours | WORK DAYS | time axis 2023-09-18 to 2023-12-31
1 | Requirement/Planning Phase |  |  |  | - |  |  | - | -
1.1 | Kickoff Project Meeting |  |  | 2023-09-17 | 2023-09-17 | 1 | 100% | 1 | 0
1.2 | Interview Questions for Key Stakeholder |  |  | 2023-09-18 | 2023-09-18 | 1 | 100% | 2 | 1
1.3 | Interview Notes |  |  | 2023-09-19 | 2023-09-19 | 1 | 100% | 2 | 1
1.4 | Refine and Review Project Scope |  |  | 2023-09-20 | 2023-09-22 | 3 | 90% | 6 | 3
1.5 | Create Work breakdown structure |  |  | 2023-09-21 | 2023-09-24 | 4 | 90% | 16 | 2
1.6 | Create Feasibility Analysis |  |  | 2023-09-22 | 2023-09-23 | 2 | 50% | 8 | 1
1.7 | Create SWOT analysis |  |  | 2023-09-23 | 2023-09-23 | 1 | 0% | 0.5 | 0
1.8 | Risk Management Plan |  |  | 2023-09-24 | 2023-09-25 | 2 | 0% | 12 | 1
1.9 | Identifying possible risks/ Risk assessing |  |  | 2023-09-25 | 2023-09-25 | 1 | 0% | 2 | 1
1.1 | Contingency Planning |  |  | 2023-09-26 | 2023-09-27 | 2 | 0% | 10 | 2
1.11 | Risk Management Documentation |  |  | 2023-09-27 | 2023-09-27 | 1 | 0% | 2 | 1
1.12 | Refine Definition of Done Template |  |  | 2023-09-28 | 2023-09-28 | 1 | 0% | 1 | 1
1.13 | Refine Definition of Done with IT team |  |  | 2023-09-29 | 2023-09-29 | 1 | 0% | 1 | 1
1.14 | Gather and understand requirements |  |  | 2023-09-30 | 2023-10-03 | 4 | 0% | 20 | 2
1.15 | Draft data dictionary |  |  | 2023-10-01 | 2023-10-01 | 1 | 0% | 5 | 0
1.16 | Write specification(Use case or user stories) |  |  | 2023-10-02 | 2023-10-02 | 1 | 0% | 3 | 1
1.17 | Create Process Flow Diagram |  |  | 2023-10-03 | 2023-10-03 | 1 | 0% | 2 | 1
1.18 | Present analysis to IT team |  |  | 2023-10-04 | 2023-10-04 | 1 | 0% | 2 | 1
1.19 | Refine specification(s) after It team review |  |  | 2023-10-05 | 2023-10-05 | 1 | 0% | 1 | 1
1.20 | Present analysis to Customer |  |  | 2023-10-06 | 2023-10-06 | 1 | 0% | 1 | 1
1.21 | Collect customer feedback |  |  | 2023-10-07 | 2023-10-10 | 4 | 0% | 20 | 2
1.22 | Refine specification(s) after customer review |  |  | 2023-10-08 | 2023-10-08 | 1 | 0% | 1 | 0
1.23 | Create Team Foundation server project folder |  |  | 2023-10-09 | 2023-10-09 | 1 | 0% | 2 | 1
1.24 | Request Active Directory groups/user permissions setup |  |  | 2023-10-10 | 2023-10-10 | 1 | 0% | 3 | 1
1.25 | Finalize data dictionary & data mapping |  |  | 2023-10-11 | 2023-10-11 | 1 | 0% | 2 | 1
1.26 | Requirements for Performance Review |  |  | 2023-10-12 | 2023-10-12 | 1 | 0% | 2 | 1
1.27 | Requirements for Quarterly Performance Review |  |  | 2023-10-13 | 2023-10-13 | 1 | 0% | 2 | 1
1.28 | Requirements for Projection/Actuals |  |  | 2023-10-14 | 2023-10-14 | 1 | 0% | 2 | 0
1.29 | Requirements for Approval |  |  | 2023-10-15 | 2023-10-15 | 1 | 0% | 1 | 0
1.30 | Requirements for Exception Handling |  |  | 2023-10-16 | 2023-10-16 | 1 | 0% | 2 | 1
1.31 | Requirements for Salary |  |  | 2023-10-17 | 2023-10-17 | 1 | 0% | 2 | 1
1.32 | Define ERD |  |  | 2023-10-18 | 2023-10-18 | 1 | 0% | 3 | 1
1.33 | Write Initial Database Scripts |  |  | 2023-10-19 | 2023-10-19 | 1 | 0% | 4 | 1
1.34 | Review Initial Database Scripts with IT team |  |  | 2023-10-20 | 2023-10-20 | 1 | 0% | 2 | 1
1.35 | Finalize site mapping |  |  | 2023-10-21 | 2023-10-21 | 1 | 0% | 2 | 0
1.36 | Review Site Mapping with IT team |  |  | 2023-10-22 | 2023-10-22 | 1 | 0% | 1 | 0
1.37 | Document final requirements |  |  | 2023-10-23 | 2023-10-23 | 1 | 0% | 4 | 1
1.38 | Review requirements with stakeholders |  |  | 2023-10-24 | 2023-10-24 | 1 | 0% | 2 | 1
1.39 | Aprroval of requirements |  |  | 2023-10-25 | 2023-10-25 | 1 | 0% | 1 | 1
1.34 | Final summary of requirements before handover |  |  | 2023-10-26 | 2023-10-26 | 1 | 0% | 3 | 1
1.35 | Project kickoff for design phase |  |  | 2023-10-27 | 2023-10-27 | 1 | 0% | 1 | 1
2 | Design Phase
2.1 | Create UI Design |  |  | 2023-10-29 | 2023-10-31 | 3 | 0% | 15 | 2
2.2 | Design UI login |  |  | 2023-10-30 | 2023-10-31 | 2 | 0% | 10 | 2
2.3 | Design perfomance review UI |  |  | 2023-10-31 | 2023-10-31 | 1 | 0% | 8 | 1
2.4 | Design quarterly perfomance review UI |  |  | 2023-11-01 | 2023-11-01 | 1 | 0% | 8 | 1
2.5 | Design performance review projections/actuals UI |  |  | 2023-11-02 | 2023-11-02 | 1 | 0% | 8 | 1
2.6 | Design performance review approval UI |  |  | 2023-11-03 | 2023-11-03 | 1 | 0% | 8 | 1
2.7 | Design performance review exception handling UI |  |  | 2023-11-04 | 2023-11-04 | 1 | 0% | 8 | 0
2.8 | Design salary projections/actuals UI |  |  | 2023-11-05 | 2023-11-05 | 1 | 0% | 8 | 0
2.9 | Design salary approval UI |  |  | 2023-11-06 | 2023-11-06 | 1 | 0% | 8 | 1
2.10 | Design salary exception handling UI |  |  | 2023-11-07 | 2023-11-07 | 1 | 0% | 8 | 1
2.11 | Review Wireframes/Mock Designs |  |  | 2023-11-08 | 2023-11-08 | 1 | 0% | 3 | 1
2.12 | Refine Wireframes/Mock Designs with IT team |  |  | 2023-11-09 | 2023-11-09 | 1 | 0% | 1 | 1
2.13 | IT team review |  |  | 2023-11-10 | 2023-11-10 | 1 | 0% | 2 | 1
2.14 | Refine Wireframes/Mock Designs after IT team review |  |  | 2023-11-11 | 2023-11-11 | 1 | 0% | 3 | 0
2.15 | Present Wireframes/Mock Designs to Customer |  |  | 2023-11-12 | 2023-11-12 | 1 | 0% | 3 | 0
2.16 | Customer Review |  |  | 2023-11-13 | 2023-11-13 | 1 | 0% | 3 | 1
2.17 | Refine wireframes/Mock Designs after Customer Review |  |  | 2023-11-14 | 2023-11-14 | 1 | 0% | 5 | 1
2.18 | End user approval UI |  |  | 2023-11-15 | 2023-11-15 | 1 | 0% | 3 | 1
2.19 | Design databse schema |  |  | 2023-11-16 | 2023-11-16 | 1 | 0% | 7 | 1
2.20 | Review ERD with IT team |  |  | 2023-11-17 | 2023-11-17 | 1 | 0% | 2 | 1
2.12 | IT team review |  |  | 2023-11-18 | 2023-11-18 | 1 | 0% | 2 | 0
2.13 | Refine ERD after IT team review |  |  | 2023-11-19 | 2023-11-19 | 1 | 0% | 1 | 0
2.14 | Write database scripts |  |  | 2023-11-20 | 2023-11-20 | 1 | 0% | 7 | 1
2.15 | Review database scripts with IT team |  |  | 2023-11-21 | 2023-11-21 | 1 | 0% | 2 | 1
2.16 | IT team review |  |  | 2023-11-22 | 2023-11-22 | 1 | 0% | 2 | 1
2.17 | Refine database scripts after IT team review |  |  | 2023-11-23 | 2023-11-23 | 1 | 0% | 1 | 1
2.18 | Implement code structure |  |  | 2023-11-24 | 2023-11-24 | 1 | 0% | 8 | 1
2.19 | Design UI development and testing |  |  | 2023-11-25 | 2023-11-25 | 1 | 0% | 8 | 0
2.20 | Design business logic |  |  | 2023-11-26 | 2023-11-26 | 1 | 0% | 8 | 0
2.21 | Design contract and validation |  |  | 2023-11-27 | 2023-11-27 | 1 | 0% | 8 | 1
2.22 | Create proxy and validation |  |  | 2023-11-28 | 2023-11-28 | 1 | 0% | 6 | 1
2.23 | Design service and validation |  |  | 2023-11-29 | 2023-11-29 | 1 | 0% | 8 | 1
2.24 | Design error handling and validation |  |  | 2023-11-30 | 2023-11-30 | 1 | 0% | 8 | 1
2.25 | Design unit testing approach |  |  | 2023-12-01 | 2023-12-01 | 1 | 0% | 7 | 1
2.26 | Design business process flow diagrams |  |  | 2023-12-02 | 2023-12-02 | 1 | 0% | 4 | 0
2.27 | Refine business process flow diagrams |  |  | 2023-12-03 | 2023-12-03 | 1 | 0% | 3 | 0
2.28 | Design functional decomposition diagram |  |  | 2023-12-04 | 2023-12-04 | 1 | 0% | 3 | 1
2.29 | Refine functional decomposition diagram |  |  | 2023-12-05 | 2023-12-05 | 1 | 0% | 1 | 1
2.30 | Design data flow diagram(s) |  |  | 2023-12-06 | 2023-12-06 | 1 | 0% | 1 | 1
2.31 | Refine data flow diagram(s) |  |  | 2023-12-07 | 2023-12-07 | 1 | 0% | 1 | 1
2.32 | Review data dictionary |  |  | 2023-12-08 | 2023-12-08 | 1 | 0% | 1 | 1
2.33 | Design use case diagram |  |  | 2023-12-09 | 2023-12-09 | 1 | 0% | 1 | 0
2.34 | Refine use case diagram |  |  | 2023-12-10 | 2023-12-10 | 1 | 0% | 1 | 0
2.35 | Review use cases |  |  | 2023-12-11 | 2023-12-11 | 1 | 0% | 1 | 1
2.36 | Create initial wireframe sketches |  |  | 2023-12-12 | 2023-12-12 | 1 | 0% | 7 | 1
2.37 | Refine user interface wireframes concepts |  |  | 2023-12-13 | 2023-12-13 | 1 | 0% | 3 | 1
2.38 | Review UI wireframes with design team |  |  | 2023-12-14 | 2023-12-14 | 1 | 0% | 2 | 1
2.39 | Refine UI wireframes based on design team's feedback |  |  | 2023-12-15 | 2023-12-15 | 1 | 0% | 2 | 1
2.40 | Create high-fidelity UI mockups |  |  | 2023-12-16 | 2023-12-16 | 1 | 0% | 4 | 0
2.41 | Validate UI mockups with stakeholders |  |  | 2023-12-17 | 2023-12-17 | 1 | 0% | 2 | 0
2.42 | Design user-friendly navigation |  |  | 2023-12-18 | 2023-12-18 | 1 | 0% | 7 | 1
2.43 | Define UI color palettte and typography |  |  | 2023-12-19 | 2023-12-19 | 1 | 0% | 5 | 1
2.44 | Ensure consistency in UI elements |  |  | 2023-12-20 | 2023-12-20 | 1 | 0% | 5 | 1
2.45 | Create responsive design for multiple devices |  |  | 2023-12-21 | 2023-12-21 | 1 | 0% | 5 | 1
2.46 | Optimize UI for accessibility |  |  | 2023-12-22 | 2023-12-22 | 1 | 0% | 6 | 1
2.47 | Incorporate user feedback into UI design |  |  | 2023-12-23 | 2023-12-23 | 1 | 0% | 7 | 0
2.48 | Develop UI style guide |  |  | 2023-12-24 | 2023-12-24 | 1 | 0% | 4 | 0
2.49 | Validate UI design against branding guidelines |  |  | 2023-12-25 | 2023-12-25 | 1 | 0% | 3 | 1
2.50 | Create interactive prototypes for user testing |  |  | 2023-12-26 | 2023-12-26 | 1 | 0% | 8 | 1
2.51 | Conduct usability testing on UI with design team |  |  | 2023-12-27 | 2023-12-27 | 1 | 0% | 8 | 1
2.52 | Finalize UI design based on testing results |  |  | 2023-12-28 | 2023-12-29 | 2 | 0% | 16 | 2
2.53 | Collaborate with development team on UI implementation |  |  | 2023-12-29 | 2023-12-29 | 1 | 0% | 8 | 1
2.54 | Document UI design decisions |  |  | 2023-12-30 | 2023-12-30 | 1 | 0% | 1 | 0
2.55 | Review and approve UI design with key stakeholders |  |  | 2023-12-31 | 2023-12-31 | 1 | 0% | 2 | 0
2.56 | Design entity relationship diagram |  |  | 2024-01-01 | 2024-01-01 | 1 | 0% | 1 | 1
2.57 | Refine entity relationship diagram |  |  | 2024-01-02 | 2024-01-02 | 1 | 0% | 1 | 1
2.58 | Refine sytsem design specification |  |  | 2024-01-03 | 2024-01-03 | 1 | 0% | 1 | 1
2.59 | Design test plan |  |  | 2024-01-04 | 2024-01-04 | 1 | 0% | 2 | 1
2.60 | Design test objectives and scope |  |  | 2024-01-05 | 2024-01-05 | 1 | 0% | 1 | 1
2.61 | Identify test requirements |  |  | 2024-01-06 | 2024-01-06 | 1 | 0% | 2 | 0
2.62 | Create test cases |  |  | 2024-01-07 | 2024-01-07 | 1 | 0% | 2 | 0
2.63 | Develop test data and test environment |  |  | 2024-01-08 | 2024-01-08 | 1 | 0% | 4 | 1
2.64 | Specify test and test environment |  |  | 2024-01-09 | 2024-01-09 | 1 | 0% | 3 | 1
2.65 | Design test metrics and key performance indicators |  |  | 2024-01-10 | 2024-01-10 | 1 | 0% | 1 | 1
2.66 | Define test entry and exit criteria |  |  | 2024-01-11 | 2024-01-11 | 1 | 0% | 1 | 1
2.67 | Plan for test automation(if applicable) |  |  | 2024-01-12 | 2024-01-12 | 1 | 0% | 2 | 1
2.68 | Design test scripts and scenarios |  |  | 2024-01-13 | 2024-01-13 | 1 | 0% | 1 | 0
2.69 | Specify test execution strategy |  |  | 2024-01-14 | 2024-01-14 | 1 | 0% | 1 | 0
2.70 | Define test reporting and documentation standards |  |  | 2024-01-15 | 2024-01-15 | 1 | 0% | 1 | 1
2.71 | Review and validate test plan with stakeholders |  |  | 2024-01-16 | 2024-01-16 | 1 | 0% | 1 | 1
2.72 | Incorporate feedback and update into test plan |  |  | 2024-01-17 | 2024-01-17 | 1 | 0% | 1 | 1
2.73 | Finalize and approve the test plan |  |  | 2024-01-18 | 2024-01-18 | 1 | 0% | 2 | 1
2.74 | Distribute test plan to the testing team |  |  | 2024-01-19 | 2024-01-19 | 1 | 0% | 1 | 1
2.75 | Prepare test environment setup instructions |  |  | 2024-01-20 | 2024-01-20 | 1 | 0% | 1 | 0
2.76 | Allocate resources for testing activities |  |  | 2024-01-21 | 2024-01-21 | 1 | 0% | 1 | 0
2.77 | Schedule test excution phases |  |  | 2024-01-22 | 2024-01-22 | 1 | 0% | 1 | 1
2.78 | Establish test data management procedures |  |  | 2024-01-23 | 2024-01-23 | 1 | 0% | 1 | 1
2.79 | Ensure Compliance with testing standards and best practices |  |  | 2024-01-24 | 2024-01-24 | 1 | 0% | 1 | 1
2.80 | Incorporate security design principles |  |  | 2024-01-25 | 2024-01-25 | 1 | 0% | 1 | 1
2.81 | Define security architectural patterns |  |  | 2024-01-26 | 2024-01-26 | 1 | 0% | 1 | 1
2.82 | Establish secure data handling practices |  |  | 2024-01-27 | 2024-01-27 | 1 | 0% | 1 | 0
2.83 | Design access control mechanisms |  |  | 2024-01-28 | 2024-01-28 | 1 | 0% | 1 | 0
2.84 | Determine Encryption requirements |  |  | 2024-01-29 | 2024-01-29 | 1 | 0% | 1 | 1
2.85 | Specify authentication methods |  |  | 2024-01-30 | 2024-01-30 | 1 | 0% | 1 | 1
2.86 | Plan for secure session maanagement |  |  | 2024-01-31 | 2024-01-31 | 1 | 0% | 1 | 1
2.87 | Outline secure communication protocols |  |  | 2024-02-01 | 2024-02-01 | 1 | 0% | 1 | 1
2.88 | Design secure error handling |  |  | 2024-02-02 | 2024-02-02 | 1 | 0% | 1 | 1
2.89 | Develop security giudelines for UI design |  |  | 2024-02-03 | 2024-02-03 | 1 | 0% | 1 | 0
2.90 | Validate design |  |  | 2024-02-04 | 2024-02-04 | 1 | 0% | 3 | 0
2.91 | Stakeholder approval |  |  | 2024-02-05 | 2024-02-05 | 1 | 0% | 1 | 1
2.92 | Complete design documentation |  |  | 2024-02-06 | 2024-02-06 | 1 | 0% | 5 | 1
2.93 | Obtain design sign-off |  |  | 2024-02-07 | 2024-02-07 | 1 | 0% | 2 | 1
2.94 | Prepare for design handover |  |  | 2024-02-08 | 2024-02-08 | 1 | 0% | 1 | 1
2.95 | Quality check and assurance |  |  | 2024-02-09 | 2024-02-09 | 1 | 0% | 5 | 1
2.96 | Check design budget alignment |  |  | 2024-02-10 | 2024-02-10 | 1 | 0% | 2 | 0
2.97 | Create design summary |  |  | 2024-02-11 | 2024-02-11 | 1 | 0% | 3 | 0
2.98 | Client review |  |  | 2024-02-12 | 2024-02-12 | 1 | 0% | 1 | 1
2.99 | Final design documentation |  |  | 2024-02-13 | 2024-02-13 | 1 | 0% | 5 | 1
2.100 | Project kickoff for development phase |  |  | 2024-02-14 | 2024-02-14 | 1 | 0% | 1 | 1
3 | Development Phase
3.1 | Review requirements |  |  | 2024-02-16 | 2024-02-16 | 1 | 0% | 1 | 1
3.2 | Refine requirements to development team |  |  | 2024-02-17 | 2024-02-17 | 1 | 0% | 1 | 0
3.3 | Review design |  |  | 2024-02-18 | 2024-02-18 | 1 | 0% | 1 | 0
3.4 | Refine design to development team |  |  | 2024-02-19 | 2024-02-19 | 1 | 0% | 1 | 1
3.5 | Develop UI code - UI Functionality |  |  | 2024-02-20 | 2024-02-21 | 2 | 0% | 16 | 2
3.6 | Develop business logic (data, equations) |  |  | 2024-02-21 | 2024-02-21 | 1 | 0% | 7 | 1
3.7 | Develop Contract |  |  | 2024-02-22 | 2024-02-22 | 1 | 0% | 5 | 1
3.8 | Develop Proxy |  |  | 2024-02-23 | 2024-02-23 | 1 | 0% | 4 | 1
3.9 | Develop Service |  |  | 2024-02-24 | 2024-02-24 | 1 | 0% | 4 | 0
3.10 | Develop Host |  |  | 2024-02-25 | 2024-02-25 | 1 | 0% | 5 | 0
3.11 | Develop Error Handling |  |  | 2024-02-26 | 2024-02-26 | 1 | 0% | 5 | 1
3.12 | Develop and run unit tests |  |  | 2024-02-27 | 2024-02-27 | 1 | 0% | 4 | 1
3.13 | Develop reports functionality |  |  | 2024-02-28 | 2024-02-28 | 1 | 0% | 3 | 1
3.14 | Create host and validate |  |  | 2024-02-29 | 2024-02-29 | 1 | 0% | 4 | 1
3.15 | Develop email functionality |  |  | 2024-03-01 | 2024-03-01 | 1 | 0% | 4 | 1
3.16 | Develop sql site map scripts |  |  | 2024-03-02 | 2024-03-02 | 1 | 0% | 5 | 0
3.17 | Review sql site map scripts with IT team |  |  | 2024-03-03 | 2024-03-03 | 1 | 0% | 3 | 0
3.18 | Run sql site map scripts |  |  | 2024-03-04 | 2024-03-04 | 1 | 0% | 3 | 1
3.19 | Validate site mapping |  |  | 2024-03-05 | 2024-03-05 | 1 | 0% | 4 | 1
3.20 | Conduct code review |  |  | 2024-03-06 | 2024-03-06 | 1 | 0% | 3 | 1
3.21 | Implement modification(if needed) |  |  | 2024-03-07 | 2024-03-07 | 1 | 0% | 3 | 1
3.22 | Address code review feedback |  |  | 2024-03-08 | 2024-03-08 | 1 | 0% | 4 | 1
3.23 | Perform code modifications |  |  | 2024-03-09 | 2024-03-09 | 1 | 0% | 3 | 0
3.24 | Review requirements of Performance Review |  |  | 2024-03-10 | 2024-03-10 | 1 | 0% | 1 | 0
3.25 | Review UI design of Performance Review |  |  | 2024-03-11 | 2024-03-11 | 1 | 0% | 1 | 1
3.26 | Performance Review pseudo code |  |  | 2024-03-12 | 2024-03-12 | 1 | 0% | 3 | 1
3.27 | Develop code for Performance Review |  |  | 2024-03-13 | 2024-03-13 | 1 | 0% | 8 | 1
3.28 | Unit testing for PR |  |  | 2024-03-14 | 2024-03-14 | 1 | 0% | 3 | 1
3.29 | Code review for PR |  |  | 2024-03-15 | 2024-03-15 | 1 | 0% | 2 | 1
3.30 | Review requirements of Quarterly Performance Review |  |  | 2024-03-16 | 2024-03-16 | 1 | 0% | 1 | 0
3.31 | Review UI design of Quarterly Performance Review |  |  | 2024-03-17 | 2024-03-17 | 1 | 0% | 1 | 0
3.32 | Quarterly Performance Review pseudo code |  |  | 2024-03-18 | 2024-03-18 | 1 | 0% | 3 | 1
3.33 | Develop code for Quarterly Performance Review |  |  | 2024-03-19 | 2024-03-19 | 1 | 0% | 8 | 1
3.34 | Unit testing for QPR |  |  | 2024-03-20 | 2024-03-20 | 1 | 0% | 3 | 1
3.35 | Code review for QPR |  |  | 2024-03-21 | 2024-03-21 | 1 | 0% | 2 | 1
3.36 | Review requirements of Projections/Actuals |  |  | 2024-03-22 | 2024-03-22 | 1 | 0% | 1 | 1
3.37 | Review UI design of Projections/Actuals |  |  | 2024-03-23 | 2024-03-23 | 1 | 0% | 1 | 0
3.38 | Projections/Actuals pseudo code |  |  | 2024-03-24 | 2024-03-24 | 1 | 0% | 3 | 0
3.39 | Develop code for Projections/Actuals |  |  | 2024-03-25 | 2024-03-25 | 1 | 0% | 8 | 1
3.40 | Unit testing for Projections/Actuals |  |  | 2024-03-26 | 2024-03-26 | 1 | 0% | 3 | 1
3.41 | Code review Projections/Actuals |  |  | 2024-03-27 | 2024-03-27 | 1 | 0% | 2 | 1
3.42 | Review requirements of approval |  |  | 2024-03-28 | 2024-03-28 | 1 | 0% | 1 | 1
3.43 | Review UI design of approval |  |  | 2024-03-29 | 2024-03-29 | 1 | 0% | 1 | 1
3.44 | Approval pseudo code |  |  | 2024-03-30 | 2024-03-30 | 1 | 0% | 3 | 0
3.45 | Develop code for approval |  |  | 2024-03-31 | 2024-03-31 | 1 | 0% | 8 | 0
3.46 | Unit testing for approval |  |  | 2024-04-01 | 2024-04-01 | 1 | 0% | 3 | 1
3.47 | Code review for approval |  |  | 2024-04-02 | 2024-04-02 | 1 | 0% | 2 | 1
3.48 | Review requirements of Exception Handling |  |  | 2024-04-03 | 2024-04-03 | 1 | 0% | 1 | 1
3.49 | Review UI design of Exception Handling |  |  | 2024-04-04 | 2024-04-04 | 1 | 0% | 1 | 1
3.50 | Exception Handling pseudo code |  |  | 2024-04-05 | 2024-04-05 | 1 | 0% | 3 | 1
3.51 | Develop code for Exception Handling |  |  | 2024-04-06 | 2024-04-06 | 1 | 0% | 8 | 0
3.52 | Unit testing for Exception Handling |  |  | 2024-04-07 | 2024-04-07 | 1 | 0% | 3 | 0
3.53 | Code review for Exception Handling |  |  | 2024-04-08 | 2024-04-08 | 1 | 0% | 2 | 1
3.54 | Review Salary requirements |  |  | 2024-04-09 | 2024-04-09 | 1 | 0% | 1 | 1
3.55 | Review Salary UI design |  |  | 2024-04-10 | 2024-04-10 | 1 | 0% | 1 | 1
3.56 | Salary UI pseudo code |  |  | 2024-04-11 | 2024-04-11 | 1 | 0% | 3 | 1
3.57 | Develop code for salary UI |  |  | 2024-04-12 | 2024-04-12 | 1 | 0% | 8 | 1
3.58 | Unit testing |  |  | 2024-04-13 | 2024-04-13 | 1 | 0% | 3 | 0
3.59 | Code review for salary UI |  |  | 2024-04-14 | 2024-04-14 | 1 | 0% | 2 | 0
3.60 | Develop salary approval UI |  |  | 2024-04-15 | 2024-04-15 | 1 | 0% | 7 | 1
3.61 | Develop salary exception handling UI |  |  | 2024-04-16 | 2024-04-16 | 1 | 0% | 7 | 1
3.62 | Develop salary projection/actual UI |  |  | 2024-04-17 | 2024-04-17 | 1 | 0% | 7 | 1
3.63 | Develop salary login |  |  | 2024-04-18 | 2024-04-18 | 1 | 0% | 6 | 1
3.64 | Optimize UI performance |  |  | 2024-04-19 | 2024-04-19 | 1 | 0% | 4 | 1
3.65 | Code optimization for production |  |  | 2024-04-20 | 2024-04-20 | 1 | 0% | 3 | 0
3.66 | Code documentation review |  |  | 2024-04-21 | 2024-04-21 | 1 | 0% | 2 | 0
3.67 | Code refactoring |  |  | 2024-04-22 | 2024-04-22 | 1 | 0% | 2 | 1
3.68 | Final unit testing |  |  | 2024-04-23 | 2024-04-23 | 1 | 0% | 3 | 1
3.69 | Development Documentation Completion |  |  | 2024-04-24 | 2024-04-24 | 1 | 0% | 5 | 1
4 | Testing Phase
4.1 | Review development, design and requirements |  |  | 2024-04-26 | 2024-04-26 | 1 | 0% | 1 | 1
4.2 | Deploy to test |  |  | 2024-04-27 | 2024-04-27 | 1 | 0% | 1 | 0
4.3 | Deploy to test environment |  |  | 2024-04-28 | 2024-04-28 | 1 | 0% | 1 | 0
4.4 | Validate functionality in test environment |  |  | 2024-04-29 | 2024-04-29 | 1 | 0% | 2 | 1
4.5 | Clean up code and comment |  |  | 2024-04-30 | 2024-04-30 | 1 | 0% | 1 | 1
4.6 | Cleanup CSS |  |  | 2024-05-01 | 2024-05-01 | 1 | 0% | 2 | 1
4.7 | Cleanup Inline Styles |  |  | 2024-05-02 | 2024-05-02 | 1 | 0% | 2 | 1
4.8 | Remove commented out/unwanted code |  |  | 2024-05-03 | 2024-05-03 | 1 | 0% | 1 | 1
4.9 | Add/Clarify comments |  |  | 2024-05-04 | 2024-05-04 | 1 | 0% | 1 | 0
4.10 | Ensure nice formatting |  |  | 2024-05-05 | 2024-05-05 | 1 | 0% | 1 | 0
4.11 | Write test cases |  |  | 2024-05-06 | 2024-05-06 | 1 | 0% | 2 | 1
4.12 | Test application |  |  | 2024-05-07 | 2024-05-07 | 1 | 0% | 4 | 1
4.13 | User acceptance testing and approval |  |  | 2024-05-08 | 2024-05-08 | 1 | 0% | 7 | 1
4.14 | Provide demo to end user |  |  | 2024-05-09 | 2024-05-09 | 1 | 0% | 3 | 1
4.15 | End user test |  |  | 2024-05-10 | 2024-05-10 | 1 | 0% | 3 | 1
4.16 | Implement modification(if needed) |  |  | 2024-05-11 | 2024-05-11 | 1 | 0% | 6 | 0
4.17 | End user approval |  |  | 2024-05-12 | 2024-05-12 | 1 | 0% | 2 | 0
4.18 | Prepare for deployment |  |  | 2024-05-13 | 2024-05-13 | 1 | 0% | 2 | 1
5 | Deployment/Implementation Phase
5.1 | Request Active Directory groups/user permissions setup |  |  | 2024-05-15 | 2024-05-15 | 1 | 0% | 1 | 1
5.2 | Create change request & folder |  |  | 2024-05-16 | 2024-05-16 | 1 | 0% | 1 | 1
5.3 | Write implemenation documentation |  |  | 2024-05-17 | 2024-05-17 | 1 | 0% | 3 | 1
5.4 | Copy sql scripts to change request folder & other locations |  |  | 2024-05-18 | 2024-05-18 | 1 | 0% | 2 | 0
5.5 | Deploy to production environment |  |  | 2024-05-19 | 2024-05-19 | 1 | 0% | 1 | 0
5.6 | Validate functionality in product environment |  |  | 2024-05-20 | 2024-05-20 | 1 | 0% | 4 | 1
5.7 | Training Plan |  |  | 2024-05-21 | 2024-05-21 | 1 | 0% | 8 | 1
5.8 | Communicate to end users |  |  | 2024-05-22 | 2024-05-22 | 1 | 0% | 3 | 1
5.9 | Develop automated test scripts |  |  | 2024-05-23 | 2024-05-23 | 1 | 0% | 2 | 1
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.
Note on J7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.

## GanttChartPro
Gantt Chart Template Pro
Gantt Chart Template Pro is similar to this free version, but
it is more feature-packed. It also comes with other bonus content.
Learn About Gantt Chart Template Pro
https://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html
The following link is a blog post that talks specifically about the
Pro version for Excel Online.
Gantt Chart Template Pro for Excel Online
Benefits and Features of Gantt Chart Template Pro
Simple Color-Coding
The Pro version includes a column for specifying the color of bars in the chart. For example,
you could change the color based on urgency or task lead.
Daily, Weekly, or Monthly View
The Pro version includes a drop-down next to the Display Week that lets you choose to display
the columns in the chart area as days, weeks, or months.
Use Work Days as an Input
By default, the Pro version is set up to have you enter Work Days instead of Calendar Days.
The expanded set of template rows provides more options for defining the Start date, End date,
and Duration of tasks. Define a task based on …
- Start date and End date
- Start date and Work days
- Start date and Calendar days
Easily Create Task Dependencies
Though you can still use your own formulas for creating task dependencies, the Pro version
includes template rows that calculate the Start date based on the WBS number that you enter
in the Predecessor column.
Exclude Holidays from Work Days
List holidays and other specific non-working days that you want to exclude from work days.
Customize Your Work Week
The versions designed for Excel 2010+ use the WORKDAY.INTL() and NETWORKDAYS.INTL()
functions that allow you define the work week as something other than Monday-Friday.
Learn More About Gantt Chart Template Pro

## Help
Help
https://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html
About This Template
This Gantt Chart Template provides an easy way to create a simple project schedule. You only need to know some basic spreadsheet operations, such as how to insert, delete, copy and paste rows and cells. For more advanced uses, such as defining task dependencies, you will need to know how to enter formulas.
Be sure to read the Getting Started Tips below. Watching the video demos for Gantt Chart Template Pro may also help you see how to use the spreadsheet.
Watch Demo Videos of the Pro Version on Vertex42.com
Please read the license agreement in the TermsOfUse worksheet to learn how you may or may not use and share this spreadsheet.
Getting Started Tips
• [Bracketed Text] is meant to be edited, like the project title and task descriptions.
| • Some of the labels include cell comments to provide extra information. | Label
• To adjust the range of dates shown in the Gantt chart, change the Display Week number.
• The Project Start Date is used to define the first week shown in the gantt chart.
• Insert new tasks using one of the methods listed below.
| • Define the task start date and duration (days) by editing the light green cells. | Input Cell
• If you see "#####" in a cell, widen the column to display the cell contents.
• Backup your file regularly to avoid losing data! Excel files get corrupted occasionally.
Inserting New Tasks (Rows)
When inserting and deleting tasks, you need to insert and delete entire rows. Some columns contain formulas (such as the End Date and the Work Days columns), so these formulas need to copied to the newly inserted rows.
METHOD 1 (recommended)
• Insert a new blank row by right-clicking on the row number and selecting Insert.
• With the new blank row selected, press Ctrl+d to copy the formulas and formatting down from the row above OR use the row drag handle to copy the formulas and formatting down.
METHOD 2
• Copy a row from the set of template rows at the bottom of the worksheet.
• Right-click on the row where you want to insert the new task and select Insert Copied Cells.
Method 2 will work, but Excel will split/fracture/duplicate conditional formatting rules rather than merging the rules. This can cause inefficiencies in very large and heavily modified files.
Help improve Excel by voting on a suggestion to fix this problem.
Using the Template Rows and Choosing a WBS Level
The set of template rows at the bottom of the Gantt Chart worksheet provide examples of different ways to format and define tasks for different WBS levels.
Each different WBS level uses a different formula in the WBS column.
You can either copy/paste/insert these template rows via Method 2 as explained above, OR you can just copy/paste the desired WBS cell when you want to change the WBS level.
If you leave a blank cell above a WBS number, the numbering will reset to 1.x.x. The formulas are meant for convenience, but you can manually enter the WBS numbers if you want to.
You can indent the task description for sub-tasks by entering leading spaces or using the Indent feature in Excel.
Creating Task Dependencies
You can enter the Start date manually, or define task dependencies using a formula. Below are some common options for defining the Start date:
A. | Enter the date manually (e.g. 1/3/2015)
B. | Reference the Project Start Date (e.g. =$E$4 )
C. | Set the Start date to the next Work Day after another task's End date.
• Use the formula =WORKDAY(enddate,1) where enddate is the reference to the End date of a predecessor task.
• For multiple predecessors, the formula would be =MAX(WORKDAY(enddate1,1),WORKDAY(enddate2,1))
D. | Set the Start date to the next Calendar Day after another task's End date.
• This formula is very simple: =enddate+1
• For multiple predecessors, the formula would be =MAX(enddate1,enddate2,enddate3)+1
E. | Set the Start date to a number of days before or after another date.
• This formula is just like the one in C or D, except that in place of the "1" you enter the number of days, such as =WORKDAY(enddate,5) or =WORKDAY(startdate,-5)
F. | Use a lookup formula and the Predecessor column to define the start date.
[The formulas for using this method are built into Gantt Chart Template Pro]
Changing the Color of the Bars in the Gantt Chart
[Advanced] The Gantt Chart is created using conditional formatting, so you can modify the conditional formatting rules to change the format to a different color. The Pro version includes a column where you can change the color by entering a color code ("b"=blue, "g"=green, etc.)
FAQs
Q: | How do I enter the Work Days instead of Calendar Days?
Entering work days instead of calendar days is a feature of the Pro version. There is nothing in the free version preventing you from entering your own formulas, though.
Q: | How do I calculate Calendar Days after entering the Start and End Dates?
You can calculate the duration in calendar days (including both start and end dates) using the formula =enddate-startdate+1
Q: | How do I change the Print Settings? (Excel 2010, 2013)
Select the entire range of cells you want to print and go to File > Print Area > Set Print Area. Then go to File > Page Setup or File > Print Preview and adjust the Scaling, Margins, and Page Orientation as desired.
Q: | How do I increase the range of dates displayed in the Gantt chart?
You will need to add columns to the right of the Gantt Chart via copy/paste. Copy and paste the columns in groups of 7. Afterwards, you will also probably need to update the print area.
Q: | How do I create a summary row that shows the MIN and MAX dates for all sub-tasks?
In the Start column, use the formula =MIN(range_of_start_dates)
In the End column, use the formula =MAX(range_of_end_dates)
In the Days column, use the formula =end_date-start_date+1
Q: | How do I calculate the %Complete for an entire category of tasks?
The %Complete for a group of tasks can be calculated from its sub tasks using the formula below, where "workdays" is a reference to the range of work day values and "complete" is a reference to the %complete for each of the subtasks.
=SUMPRODUCT(workdays,complete)/SUM(workdays)
Example: Let's say you have 3 sub tasks that are 10 days, 12 days, and 14 days long, respectively. If the first subtask is 50% complete and the others are 25% complete, you could calculate the overall percent complete for the group as: =(10*50%+12*25%+14*25%)/(10+12+14).
Q: | I've messed up the chart area somehow. How do I fix it?
Find a row that works, then copy the cells that make up the gantt chart area from that row into the row that is messed up.
© 2006-2018 Vertex42 LLC
Note on C16: This is an example comment.

## TermsOfUse
Terms of Use
Gantt Chart Template, by Vertex42.com
https://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html
© 2006-2018 Vertex42 LLC
This spreadsheet template, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
You may download the spreadsheet template, make archival copies, and customize the template only for your personal use or use within your company or organization and not for resale or public sharing.
You may not remove or alter any Vertex42 logo, trademark, copyright, disclaimer, brand, terms of use, attribution, or other proprietary notices or marks within the template.
The template and any file, document, or other work including or derived from the template may NOT be sold, distributed, published to an online gallery, hosted on a website, or placed on any server in a way that makes it available to the general public.
Limited Private Sharing and Other Allowed Uses: See the complete license agreement to learn more about how you may or may not use this template.
View the Complete License Agreement
https://www.vertex42.com/licensing/EULA_privateuse.html